## Gantt
[5 empty] | Trimester 1 (2026) | [13 empty] | Trimester 2 (2027)
Task | Start | End | Status | Type | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | Break | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
[5 empty] | 31 Aug | 7 Sep | 14 Sep | 21 Sep | 28 Sep | 5 Oct | 12 Oct | 19 Oct | 26 Oct | 2 Nov | 9 Nov | 16 Nov | 23 Nov
Literature review and project proposal | T1 W1 | T1 W8 | In progress | Task | bar: 31 Aug to 19 Oct
Requirements and review of SSMC records | T1 W1 | T1 W3 | Completed | Task | bar: 31 Aug to 14 Sep
Data model design | T1 W2 | T1 W4 | Completed | Task | bar: 7 Sep to 21 Sep
Application build (HV overview, SLD generation) | T1 W3 | T1 W7 | Completed | Task | bar: 14 Sep to 12 Oct
Breaker status, maintenance records, history | T1 W7 | T1 W7 | Completed | Task | bar: 12 Oct
Named user logins and hosted demonstration | T1 W9 | T1 W12 | Planned | Task | bar: 26 Oct to 16 Nov
Data entry of LVSB room records | T1 W10 | T2 W3 | Planned | Task | bar: 2 Nov to 23 Nov
On-site verification of 10 entries | T2 W2 | T2 W4 | Planned | Task
Poster preparation | T2 W2 | T2 W4 | Planned | Task
Timed lookup evaluation | T2 W5 | T2 W7 | Planned | Task
Refinement from evaluation results | T2 W6 | T2 W8 | Planned | Task
Final technical report | T2 W6 | T2 W12 | Planned | Task
Assessment milestones
Project proposal (25 Oct) | T1 W8 | T1 W8 | Milestone | Milestone | bar: 19 Oct
Poster presentation | T2 W4 | T2 W4 | Milestone | Milestone | [17 empty] | ◆
Final demonstration | T2 W9 | T2 W10 | Milestone | Milestone | [22 empty] | ◆ | ◆
Final technical report | T2 W12 | T2 W12 | Milestone | Milestone | [25 empty] | ◆
Legend
Completed
Planned / in progress
Assessment deadline